## Sheet1
WBS Number | Task Name | WBS Description | Must Start by Date | Must End by Date | Task Level of Effort (in hours) | Task Duration (in days) | Predecessor (Finish-to-Start Dependency) (comma separated) | Resource Name(s) | Author (of Item for follow-on questions)
1 | Menu management system | Menu development is a major component for the restaurant management system. It will include all the food items, their images and their costs. | 2021-10-16 | 2021-10-19 | 6 | 3 |  | HTML,CSS | Khushi
1.1 | Add | Menu will need to be updated daily based on when a food item needs to be added, deleted or their price or any detail needs to be updated | 2021-10-31 | 2021-11-10 | 15 | 8 | 1 | php/js/python | Uditi
1.2 | Delete
1.3 | Updation
1.4 | Add category | If a new food category has to be added, the admin can add it.
1.5 | Delete product | If a product needs to be deleted because of availability or any other reason
1.6 | Updation product | Product details can be updated.
2 | Order retrieval system | Retrieval of orders so that the employees can work on them
2.1 | Retrieve new orders | New orders should be retrieved from the database based on the orders. | 2021-11-15 | 2021-11-20 | 7 | 4 | 1 | sql | Khushi
2.2 | Display orders | Order will be displayed under "My account" option for every customer
3 | Login/ Signup page | For the customers to order and pay and to keep a track of their order
3.1 | Login page | It will ask the user to fill in their username and password. | 2021-11-25 | 2021-11-30 | 10 | 5 |  | html,css | Uditi
3.1.1 | Forgot password | An option to change password in case user forgets their password.
3.2 | Sign up page | It will ask user to fill name, email, password and contact number
3.2.1 | Social media | Can also signup using google or facebook
4 | Payment and delivery | Payment form is generated ionce the customer has added all items in cart and clicked proceed
4.1 | Bill | If the customer has logged in then the bill will be displayed with the description of the food articles ordered as soon as customer clicks proceed to pay and their costs and the delivery charge. | 2021-12-01 | 2021-12-04 | 5 | 2 | 1,2 | payment getaway | Khushi
4.2 | Delivery | Once the payment is done, the delivery person will come to pick up the product and will then deliver it. the customer can track their order